Table of Contents

Executive Summary	2

Chapter 1:  Introduction To Missouri Project Oversight	3

1.1 Program Background	3

1.2 Project Oversight Definition	5

1.3 Program Scope	6

1.4 Program Approach	6

1.5 Program Benefits	7

Chapter 2: Terms and Definitions	9

Chapter 3:  Project Oversight Program Administration	10

3.1 Program Relationships	10

3.2 Program Governance	10

3.3 Roles and Responsibilities	11

Chief Information Officer (CIO)	11

Office of Information Technology	11

Project Oversight Controller	12

Project Oversight Manager	12

Project Oversight Committee/Project Oversight Reviewer	13

Agency Project Manager	13

Contractor Project Manager	14

Project Team	14

Chapter 4:  Program Methodology	15

4.1 Project Oversight Functions	15

4.2 Rules of Thumb	15

4.3 Oversight Project Model	16

4.3.1 Focus on Project Artifacts	16

4.3.2 Project Model Organization	16

Monitor & Measure	17

Accountability	17

4.4 Oversight Levels	17

4.5 Oversight Processes & Templates	18

Oversight Initiation Process	21

Oversight Planning Process	21

Oversight Implementation Process	22

Oversight Closeout Process	22

Oversight Vitality Process	22

# Executive Summary

The Missouri Project Oversight Program Manual presents the guidance and approach for implementation of the Missouri Project Oversight Program including the background, definition, and justification for the program as well as the processes, templates, and associated narratives necessary to support program implementation.  The manual presents this information in two parts:

Part I – Project Oversight Program Administration

Part II – Project Oversight Processes and Templates

Part I - Project Oversight Program Administration provides the introduction to the Missouri Project Oversight Program, defines project oversight, defines program scope and approach, and identifies the program benefits.  In addition, Part I provides information on program relationships, program governance, and the program methodology including introduction to the oversight levels and the processes and templates used during program implementation.

Part II – Project Oversight Processes and Templates includes and overview of the project oversight methodology, the process models and detail for the oversight processes as well as specific templates, which are completed during the oversight processes.

# Chapter 1:  Introduction To Missouri Project Oversight

Chapter 1 offers an introduction to the Missouri Project Oversight Program.  The Chapter identifies the program background, the definition of project oversight, the scope of the program, the program approach and identification of the program benefits to the State of Missouri.

## 1.1 Program Background

The Office of Information Technology (OIT) was created in July of 1995 as a result of Governor Carnahan’s Commission on Management and Productivity.  One responsibility identified as part of the OIT mission was the development and implementation of an Information Systems Strategic Plan.  The initial version was completed in June 1996 and a number of updated versions have been generated since the original plans inception.  The new version of the plan continues to focus on issues such as improved delivery, efficiency and accessibility of government services.

In support of the strategic plan, the OIT in partnership with the Information Technology Advisory Board (ITAB) introduced into Missouri state government a formal project management methodology, with project management training and certification. Collectively these administrative bodies oversee and monitor progress and achievements of state technology projects.

While Missouri state government is committed to the concept of project management and has put in place implementation guidelines, sound project management can only be complete by closing the loop with an effective project oversight program.  One that balances the effectiveness of the project plan by evaluating how well the project is doing at achieving performance goals and objectives.

This program provides the basis for the development of a project oversight methodology which when realized will fulfill its mission of bringing about a high degree of quality and efficiency in Missouri’s business and technology projects, and provides an efficient and effective means to share “best practices”, “lessons learned” and other information on project management and oversight with the state’s IT community.

## 1.2 Project Oversight Definition

This document describes the State of Missouri’s Project Oversight Program.  It is also intended to provide a common understanding of the various roles and responsibilities of project oversight in relationship to other management disciplines such as project management, risk management and cost management. Understanding the different role perspectives between project management and project oversight is critical to understanding the oversight program.  Table 1.2-1 illustrates the key roles and the perspectives for each role for both project management and project oversight.

| PROJECT OVERSIGHT VS PROJECT MANAGEMENT |
| --- |
| Role | Project Management | Project Oversight |
| Project View | Detailed task level view | Product/Deliverable and Process view |
| Focus | Direct project related activities | Monitor: Direct project activities Outside influences impacting project |
| Quality Assurance Function | Should not perform your own QA Deliverable accuracy which points to quality of process execution | Independent 3rd party QA Deliverable content which points to quality process existence |
| Key Activities | Provide: Planning Leadership Organization Control | Assist: Maintaining “big picture” view of project Maintain project scope Proactive Problem/Issue Identification & Avoidance Adding insight into issue prioritization and resolution |
| Decisions | Decision making authority | Decision support |
| Additional Activities |  | Project manager coaching/mentoring |

Table 1.2-1, Project Oversight vs. Project Management

Project management is an integrative endeavor – an action, or failure to take action, in one area will usually affect other areas.  The interactions may be straightforward and well understood, or they may be subtle and uncertain.  For example, a scope change will almost always affect project cost, but it may or may not affect product quality.  These interactions often require trade-offs among project objectives, such as; sacrificing performance in one area may enhance performance in another.  Successful project management requires actively managing these interactions.

Project oversight describes the processes required to ensure that these interactions are being managed successfully, and that the project will satisfy the needs for which it was intended.  It stands separate from these other management functions in that it does not have the same front-line direct responsibility for the successful definition and implementation of a project, but rather acts in a check-and-balance capacity to the other functions.  It consists of selected actions, dependant upon project oversight levels, to ensure proper outcomes.

In order to develop this oversight program, a common definition and understanding of project oversight is necessary.  The definition of project oversight that will be used for this program is:

Evaluating and communicating overall project performance on a regular basis to provide confidence that the project will satisfy the intended business result and be completed on time and on-budget.

## 1.3 Program Scope

The Missouri Project Oversight Program is being developed to support the State’s Project Management Program and encompasses all Missouri State Government information technology projects.  Missouri State Government has acknowledged the importance of the oversight program by initiating an administrative agreement between OIT and Department of Budget and Management in the Office of Administration mandating a project budget line item of three to four percent of the total project budget designated specifically to fund project oversight efforts.  Various “levels” of oversight are established to determine the personnel requirements as well as the depth and intensity of the oversight program as it is applied to information technology projects.

## 1.4 Program Approach

The Information Technology Advisory Board (ITAB) is responsible for adopting statewide information technology policies, standards, procedures, methodologies, IT Architecture and strategic plans for the State of Missouri.  ITAB is also responsible for proposing information technology policies and procedures, project management methodologies, an information technology architecture, standards for data management and a strategic information technology management plan.

The ITAB has implemented a standing committee for Project Management to address issues critical to information technology project management in the State. Subcommittees within the Project Management Standing Committee (PMSC) have been established to address Project Oversight, Total Cost of Ownership/Return on Investment, Risk Management, and Performance Metrics.  Figure 1.4-1 illustrates the ITAB committee relationships that relate to Project Oversight.

Figure 1.4-1, ITAB Committee Relationships

The Project Oversight Program and the project oversight methodology defined in this manual set is the result of the combined efforts of the Missouri Office of Information Technology (OIT) and National Systems & Research Co. (NSR). The combined salient features of NSR’s oversight methodology adapted for Missouri and refined during the CIMOR Project Oversight Pilot Project, and the initial draft of the Missouri Project Oversight Program developed by OIT has resulted in a combined Project Oversight Program and manual set that incorporates all the best processes, policies, and artifacts contained in both approaches.

## 1.5 Program Benefits

The IT Strategic Plan identifies a set of values that represent the guiding principles and standards of the Missouri State Government Information Technology community.  These values contribute to and support the goals and objectives in the plan. Of those values identified, three relate significantly to the Project Oversight Program and are projected into the development and implementation of the Project Oversight Program.  The three values restated are as follows:

ACCOUNTABILITY – We are accountable to the citizens of Missouri and will conduct our business in a fiscally responsible manner.

COOPERATION – We believe that cooperation between state entities is fundamental to our work and we will consciously strive to share resources and work together.

EFFECTIVENESS – We believe the effectiveness of our services is crucial and needs to be balanced with the efficiency of operations.

Again, the IT Strategic Plan key area of focus for project oversight is Optimization, defined, as “The effective and efficient utilization of state resources is necessary to support the mission of the state. Our goal is to create and support an operational environment where costs are managed, resources are shared and used to their maximum potential, and services are continually improved”.

The Project Oversight Program when implemented will help to ensure the effective and efficient utilization of state resources. Oversight of project management will help ensure costs are managed and resources are used to their maximum potential. Essentially, project oversight facilitates project success by assessing project management practices to help ensure that the right things are done, and that things are done right.  Project oversight acts as a check-and-balance for project management processes such as risk management, quality management, cost management, resource management, change management, contract management and procurement management.

More specifically, project oversight operates by verifying or, where appropriate taking direct steps to help ensure that projects:

- Are structured and managed in accordance with the State of Missouri’s established standards and best practices

- Are implemented in compliance with all relevant processes, conditions and requirements

- Progress in accordance with approved project plans and requirements

- Achieve defined success factors and obtain expected results

Together the Office of Information Technology and the Information Technology Advisory Board have made integrating the principles of quality into technology projects a top priority by instituting formal project oversight criteria.  This program offers a very real opportunity to ensure sound management and stewardship of the state’s resources as the states’ business and technology community focus on quality initiatives.  In general, project oversight is most concerned with those management actions and activities that can reasonably be done and should be done to successfully implement projects in Missouri State Government.

# Chapter 2: Terms and Definitions

The Information Technology industry has developed its own unique terms for explaining components and functions specific to the industry.  These terms have a specific meaning for their users and become a tool for referring to programs, processes, products or technologies that can be extremely complex.  Many terms can have multiple meanings and the context that the term is used in is typically critical to understanding the intent of the reference.

A list of terms and conditions used to describe this program and manual set is presented here to improve the reader’s understanding of the program.  This terminology has been aligned with the terminology already reviewed and accepted by the Missouri State IT Community through the review and acceptance of the Missouri Adaptive Enterprise Architecture Manual.

| MPOP | Missouri Project Oversight Program |
| --- | --- |
| Artifact | Any form of information (formal documents, spreadsheets, notes, memos, etc) or element of a product/service that is produced in support of a project or as a result of the project execution. This includes organization information, information required by management, project descriptions, product descriptions, and all project deliverables |
| Deliverable | Project deliverables are a subset of all project artifacts. They are made up of all products that are produced as a direct result of project requirements. While artifacts can include sources of information that simple supports a project, deliverables are only produced through execution of the project. |
| Project Model | A view of a project that organizes and enables management of project information. |
| Oversight Project Model (OPM) | The key tool used for MPOP, which provides a view of the project that keys on the project deliverables. This tool allows the oversight to manage the project artifact/deliverable information and provide effective oversight support. |
| Oversight Baseline Model | This model provides a superset of all artifacts/deliverables that might possibly be a part of an IT project. This model is used as a checklist to ensure that a project has identified all necessary artifacts/deliverables given it’s unique characteristics. |
| Product/Service | The ultimate result of project execution. This will typically be application software and supporting hardware, or a service provided through the use of software/hardware. The OPM organizes project deliverables in a hierarchy, with a top level of “Product/Service”. |
| Product Component | The second level in the OPM deliverable hierarchy. A product component is simply a logical grouping of deliverables that serve a common subject area. In the hierarchy, one or more product components makes up a product/service |
| Deliverable Attributes | For each deliverable listed in the OPM there is associated information that aides monitoring and evaluating performance and quality for the deliverable. This includes quality factors, dependencies, responsible party, status, and deliverable requirement. |

# Chapter 3:  Project Oversight Program Administration

Chapter 3 identifies the administration aspects of Missouri’s Project Oversight Program.  The Project Oversight Program includes terminology, processes, templates, organizations, roles, responsibilities, functions, and relationships that define it. This Chapter describes the Project Oversight Program Administration consisting of program relationships and Program Governance including identified roles and a description of the responsibilities specific to the Oversight Program for each of the roles.

## 3.1 Program Relationships

The Missouri Project Oversight Program does not stand on it’s own. It has dependencies or associations with three other programs that currently exist or are being developed, Missouri’s Project Management Methodology, the Missouri Adaptive Enterprise Architecture (MAEA), and the Missouri Risk Management Program. Each of these plays a role in the planning and execution of the oversight program.

To ensure that projects are conducted in a disciplined, well-managed and consistent manner, Missouri state government established a Project Management Methodology (PMM) and a reporting process for all information technology projects.  The current project management methodology is documented in the State of Missouri Project Management Best Practices Reference Manual. This methodology, when properly executed, provides a basic structure for understanding project management and applying that knowledge to project activities to promote the delivery of quality products and services on-time and on-budget.

In addition to project management guidelines and best practices, Missouri is developing an adaptive enterprise architecture that facilitates business system sharing across departmental lines of responsibility.  Missouri’s enterprise architecture provides a consistent strategy for planning and implementing technology solutions throughout state government, ensuring effective use of state resources and money, and provides for consistent, effective delivery of services.

Through the establishment of principles of governance, and the declaration of technology preferences and standards to guide product selection and ensure solution interoperability across the enterprise, this systemic framework enhances the State’s ability to manage technology investments and decisions related to strategy, business goals, information needs, data mapping and selection of specific hardware and software.

The risk management program exists to provide a standardized approach to IT project risk assessment for Missouri IT projects. An understanding of project risks is critical to an accurate determination of the level of oversight needed on a project. It is through the provision of risk information that the risk management program supports project oversight.

These initiatives, along with the Project Oversight Program, provide the environment to help the state achieve a high degree of accountability and creditability for proposed business systems; and for project planning, execution and closeout.

## 3.2 Program Governance

The Missouri Project Oversight Program is governed by a well-defined set of roles, responsibilities and processes.  These areas must be well managed to ensure the effectiveness of the Oversight Program.  This section identifies the governance structure for the Missouri Project Oversight Program and includes a listing of all the key personnel and organizations that play a role in the project oversight program. It also gives a brief description of the responsibilities for each of the roles identified.  Figure 3.2-1, Missouri Project Oversight Program Governance Structure identifies the relationships between the key roles and management responsibilities for the Missouri Project Oversight Program.

Figure 3.2-1, Missouri Project Oversight Program Governance Structure

## 3.3 Roles and Responsibilities

The support the Project Oversight Program requires the involvement of personnel in a variety of roles and responsibilities.  The following provides the narrative description of the identified roles and responsibilities for the Missouri Project Oversight Program.

#### Chief Information Officer (CIO)

Champions the Missouri project oversight effort, promotes the value of the oversight program, ensures oversight success, and assigns appropriate resources out of the Office of Information technology to support the Project Oversight program development and implementation.  Has IT project approval for large budget projects and supports the budget and appropriation process on behalf of other agencies.

#### Office of Information Technology

Working with the State Project Oversight Committee, the Office of Information Technology (OIT) will serve as the focal point for the Project Oversight Program by supporting the development of policy and providing reviews for project oversight compliance.  OIT will continue to identify processes, procedures and mechanisms to improve the probability of a successful project delivered on time and within budget.

At the request of the Office of Administration, Division of Budget and Planning, 4% of an agency’s approved appropriation request will be funded to provide for project oversight services.  Those designated funds will be managed by OIT with the responsibility of determining appropriate use of those funds by the agencies.  Final approval for payment of project oversight services will be made by OIT upon receipt of agency invoices.

Specific responsibilities for the Office of Information Technology include:

- Developing the Oversight Contractor services Project Assessment Quotation (PAQ) in cooperation with state agency

- Issuing the PAQ contract release

- Receiving and reviewing Oversight Contractor invoices for services performed

- Submitting interagency invoices to state agency for Oversight Contractor services performed

- Receiving and reviewing annotated oversight reports

- Serving as arbitrator with the Oversight Contractor and the agency

- Ensuring compliance with the Project Oversight Program policies

- Ensuring that risk management is being iteratively applied

- Facilitating the application of lessons learned to other business and technology projects

#### Project Oversight Controller

The Oversight Controller resides in the Office of Information Technology (OIT) and provides control of the entire, statewide project oversight program. Communications to and from all oversight managers and OIT are channeled through the oversight controller. Oversight controller responsibilities include:

- Selection and appointment of all oversight managers to the various state projects.

- Provision of all MPOP manuals and documentation to oversight managers

- Management of oversight managers to ensure compliance with the MPOP policies, procedures, and processes.

- Collection of monthly status reports for all projects receiving oversight services

- Rollup of all oversight project status for OIT reporting purposes

- Managing the vitality of the program including the promotion of MPOP process improvement

#### Project Oversight Manager

Large and complex projects and projects with high visibility often require additional oversight to ensure the project remains on track and within scope. This oversight helps ensure the early identification and resolution of issues and the achievement of the expected business results. It is the responsibility of the Oversight Manager to manage this process.

The Oversight Manager is responsible for monitoring, evaluating and reporting on the following:

- Accurate reporting on the general status of the project

- Accurate reporting on the financial status of the project

- Adherence to the high-level work plan for the project

- The attainment of on-time and on-budget milestones or benchmarks

- The completion of the project and the realization of the expected business goals

- Assessing quality of processes and products

It is also the oversight manager’s responsibility to ensure that the oversight process is properly implemented and that it is well communicated to all stakeholders, the project manager, and the oversight committee members. Expectations for project oversight must be clearly set at the outset of the project. It is necessary that the Oversight Manager be given sufficient authority to drive the oversight process to ensure its successful implementation through cooperation by all parties.

#### Project Oversight Committee/Project Oversight Reviewer

The initial determination of the oversight level will dictate whether a specific Project Oversight Committee or an Oversight Reviewer is designated for the project.  Both essentially fulfill the same role. For higher risk projects with a higher level of oversight, an oversight committee will be assigned. For lower risk projects with a lower level of oversight, the project reviewer assumes the roles and responsibilities of the Oversight Committee. A primary project stakeholder, typically a member of agency executive management, will fill the role of oversight reviewer.

The oversight committee will be a required decision making body on the larger more complex projects requiring higher levels of project oversight. It is made up of key stakeholders with a vested interest in the outcome of the project. This may include internal agency management, outside agency groups, key user groups, and/or any other organization representative concerned about the project’s success. The purpose of the committee is to help steer the direction of the project and provide critical decision-making support as projects risks and issues are reported. The following are the responsibilities identified for the oversight committee and/or the Oversight Reviewer:

- Attend regularly scheduled oversight committee meetings (usually held monthly)

- Monitor project progress as reported by project oversight manager

- Assess and discuss project risks and benefits

- Provide decision making authority at an executive level

- Generate recommended project improvement courses of action as a result of a significant risk event.

It is important that the oversight committee and/or the Oversight Reviewer be empowered with executive decision making authority and plays an influential role in the decisions that drive the project. Without this authority, the overall effectiveness of the oversight process will be greatly reduced.

#### Agency Project Manager

It is the responsibility of the agency project manager to ensure that information developed concerning the quality and effectiveness of the project plan is appropriately evaluated, action plans developed, reports distributed and actions taken.  Project communications are primarily the responsibility of the agency project manager because they are the central figure to the project. The overall execution of the project, production of all deliverables, adherence to schedule, adherence to budget, and management of processes fall into his realm of responsibility. While the oversight manager is responsible for the oversight processes, the agency project manager is key to its success or failure.  The project manager has an obligation to evaluate and annotate the status reports with his or her comments.  The annotated report will then be distributed to appropriate parties. Appropriate parties will vary depending upon the level of oversight.

#### Contractor Project Manager

It is the responsibility of the contractor project manager to lead, manage, and control the efforts of the contractor technical team. The execution of the contractor’s portion of the project, production of all deliverables, adherence to schedule, adherence to budget, and management of processes fall into the contractor project manager’s realm of responsibility. From a quality standpoint the primary concerns are with deliverable quality and that they meet the requirements mandated by the state agency. Communications between the agency and the contracting firm are channeled through the contractor project manager.

Within the oversight methodology, the contractor project manager will be involved in reviewing and confirming the list of required project deliverables with the agency project manager and the oversight manager. He will provide status on all deliverables and participate in the resolution of project issues that fall under the responsibility of the contracting firm. The contractor project manager will also participate in the Oversight Committee meetings (if applicable).

#### Project Team

The project team is comprised of all management and technical staff that is directly involved in the development and/or implementation of the project deliverables. This includes agency and contractor personnel. The project team responsibilities include the production of deliverables, execution of project processes, and resolution of project issues.

# Chapter 4:  Program Methodology

The Project Oversight Program is based on an overall methodology including the processes and templates that support it. This Chapter provides a high-level introduction to the methodology and the supporting processes and templates to provide an overall view of the program without moving into the details. The details are provided in Part II of this manual.

## 4.1 Project Oversight Functions

The oversight program plays a quality assurance role. Quality assurance can be defined in many ways and can involve many different ideas and activities in various subject areas. Project oversight quality assurance activities as defined in this program include:

- Plan – initiate the oversight process and develop and/or configure the tools necessary to perform project oversight. Communicate and organize the oversight process and initiate all oversight activities.

- Monitor – using the oversight tools developed during the planning process, monitor all aspects of the project to generate an understanding of the overall project health.

- Evaluate – assess project risks and issues to enable proper business decision making by stakeholders

- Communicate – obtain and disseminate project information to the project manager and other stakeholders to help keep all parties abreast of project issues.

- Project Manager Support – key to successful implementation of the oversight process is building a partnering relationship with the project manager. Support of the project manager will help ensure that all elements of the project receive needed attention.

## 4.2 Rules of Thumb

The following is a set of general guidelines recommended for the oversight program. These are not necessarily mandatory requirements of project oversight, but they are considered important to oversight success and ultimately project success:

- Whenever possible, begin project oversight at the beginning of the project.

- Be flexible when implementing the oversight process. As much as possible the oversight process should work in harmony with the established agency environment.

- Project oversight should be limited to the above functional areas. The oversight manager’s activities should not include the design, definition, or creation of system components or project deliverables. This is important because it allows the oversight manager to remain an objective third party participant in the project.

- It is best if the oversight manager becomes a partner to the project team and plays a visible part in the success of the project.

- It is very important that the oversight program be viewed as a beneficial service to the project as opposed to a watchdog whose only role is to find problems and pinpoint the blame.

- The project manager should become familiar with project processes such as the development lifecycle, procurement, risk assessment, etc. This will better enable him to assess project performance and health.

## 4.3 Oversight Project Model

The primary goal for the Project Oversight Program is to provide an external means to view an information technology project in a clear and concise way providing the ability to support the project manager, make decisions, and guide overall project performance.  The methodology is centered on the creation of a Project Model for tracking project condition and status that makes project oversight an efficient, repeatable, maintainable, consistent, and flexible process. This goal is not always easily reached on large, complex projects. These projects can involve the efforts of multiple project managers, numerous technical staff members with widely varying expertise, the development of numerous deliverables, the management of remotely located contractors, the implementation of a complicated software development methodology, and the use of unfamiliar technologies.

These elements of complexity are driven directly or indirectly by requirements that are typically derived from multiple sources (Contract, RFP, Contractor Proposal, Implementation Plan, PAQs, etc.). This Project Oversight methodology helps to minimize the inherent complexity of the project by providing a means to organize and coordinate the requirements that are found in each of the sources thereby making them more manageable. Again, central to this methodology is a tool, the Oversight Project Model that has been developed to provide a single source for all project oversight information, organize the information, reduce the information’s complexity, and communicate the information effectively. Implementing the Project Model greatly enhances the ability to support the project manager, make decisions, and guide the overall project.

### 4.3.1 Focus on Project Artifacts

A key step in successfully performing project oversight is identifying products and services that are measurable and capable of being monitored for performance. This leads to a focus on the project artifacts including documents, software components, models, plans, etc. Artifacts are the tangible aspects of a project, many of which are contractually required as deliverables. They are measurable in regards to quality and completeness by examining their content. In addition, since the ability to develop an artifact implies that work has been performed, they also provide a means to monitor the project’s progress by assessing the timeliness of artifact completion compared to scheduled milestones. All areas of a project require the development of artifacts, so it is through the focused attention on artifacts that project performance can be measured and quality assured.

It is important to note that this document will make references to both deliverables and artifacts. While deliverables are actually a type of artifact, they are the key measurable artifacts that will be tracked throughout the project. Because of this, these terms are interchangeable as they are presented here.

### 4.3.2 Project Model Organization

The Project Model is the organized collection of all artifacts (products, services, deliverables, etc) that define the project. Because the artifacts can be numerous and can be collected from a number of sources, the Project Model is needed to bring all the artifact information together to provide a clear identification of all products, services and deliverables for the project as a whole. This information is organized in a hierarchy as depicted in Figure 4.3.3-1. The products/services are comprised of a set of components, which are essentially categories under which the various deliverables are listed. This hierarchy of Product/Service to Component to Deliverable is used throughout the Project Model.

Figure 4.3.3-1, Project Model Structure

Besides providing a clear view of the project, the project model also includes information associated with each deliverable that allows for the ability to monitor it, measure it, and ensure accountability. These are referred to as Artifact Attributes. These include:

Monitor & Measure

- Dependencies – deliverables or other artifacts that must be delivered before this deliverable can be completed

- Status – the current state of the deliverable

- Quality Factors – Expected elements that should be found in the final deliverable

Accountability

- Evidence of completion – evidence that the deliverable has been completed

- Deliverable requirements source – the document or other source that identified the deliverable

- Responsible party – the person or organization that is responsible for the deliverables development.

All of this information is very important to the oversight methodology. It not only provides the ability to proactively monitor the project performance, but also the ability to identify risk in a timely manner, and perform a first level of quality assurance.

## 4.4 Oversight Levels

Recognizing that every state agency and every IT Project is unique, the Missouri Project Oversight Program (MPOP) will not attempt to deploy a ‘canned’ approach that meets the needs of every agency or every project.  Virtually all projects require some level of oversight.  Some may require project oversight or review administered by a formal structure; others may be more informal. Some may require validation by an independent third party; others may only require validation by internal agency personnel. The decision on what level of oversight to implement is based on a number of factors that essentially define the importance of the project.  The identification of an appropriate level of project oversight is critical to ensuring that proper processes and tools are applied by the oversight methodology.

The oversight level is used to determine two aspects of project oversight:

- The oversight management and reporting structure

- The oversight information demands

- Status Review Frequency

The Office of Information Technology in conjunction with the project stakeholders makes a decision as to whether or not an independent project oversight manager is necessary for a particular project.  Following this determination, the oversight manager with the assistance of the agency project manager determines the level of oversight that is appropriate for the project.  This decision is reviewed, adjusted if necessary, or confirmed as the Project Oversight Initiation Process is completed.

The Office of Information Technology in conjunction with agency management determines the level of oversight that is appropriate for the project. This sub-process step utilizes an Oversight Level Matrix provide a somewhat objective means of determining the oversight level for the project. Using the internal and external risk assessment information from the Oversight Level Questionnaire, this matrix provides a somewhat objective means of determining the oversight level.

Oversight Level Matrix

Based on the level of internal and external risk, the table provides a value that identifies the project’s oversight level. This level is then used to determine the appropriate oversight information demands, oversight management and reporting structure, and oversight status review frequency. These are described in the Oversight Planning Process, Develop Oversight Plan sub-process.

## 4.5 Oversight Processes & Templates

The Oversight Methodology includes processes, sub processes, templates, and associated narratives that enable the oversight manager to perform the functions of project oversight to the benefit of Missouri’s IT initiatives. The processes and templates covered in Project Oversight Manual Part II, Chapters 1 – 4 are introduced here with a high-level description in the order that follows the flow of the oversight activities.

There are five primary processes that support the Project Oversight Program.  These five processes include the Oversight Initiation Process, Oversight Planning Process, Oversight Implementation Process, Oversight Closeout Process, and the Oversight Program Vitality Process.  Figure 4.5-1, Project Oversight Methodology Overview presents the five primary processes of the oversight methodology. The processes flow into each other in waterfall fashion starting with Oversight Initiation and ending with the Oversight Vitality Process feeding process improvement back into the program.

Figure 4.5-1, Project Oversight Methodology Overview

Each of these five primary processes is supported by a number of sub processes and templates that facilitate execution of the Project Oversight Program.  Figure 4.5-2, Oversight Processes and Templates, identifies the sub processes and templates including their association with other processes and templates.

(The Vitality Process is TBD at this time.)

Figure 4.5-2, Oversight Processes and Templates

The detailed process models and templates including associated narratives are presented in Chapters 1-4 along with the associated detailed narratives. The following provides a high-level introduction of the five primary processes.

#### Oversight Initiation Process

The Oversight Initiation Process has the primary objective of ensuring that the oversight manager gains a strong understanding of the project and its potential risk areas. To make this possible this process includes the accumulation of project documentation that will be used throughout the life of the project. Included is an initial identification and analysis of critical project information, which results in an understanding of the project risks. The oversight methodology relies upon this information and analysis to identify and configure the oversight toolset.  The Oversight Initiation Process is supported by a number of sub processes and templates.  The sub processes and templates that support the Oversight Initiation Process are as follows:

Sub Processes

- Initial Oversight Level Qualification

- Project Information Analysis

- Complete Project Information Template

Templates

- Project Information Template

#### Oversight Planning Process

Planning is critical to the success of any endeavor and project oversight is no exception. The Oversight Planning Process starts with the development of an oversight strategy and an oversight plan, each of which are key products derived using the results of the analysis of project information obtained during the Oversight Initiation Process. It also involves perhaps the most important step of the methodology, development of the Oversight Project Model (OPM).  The OPM is the key tool used during the Oversight Implementation Process. Finally all oversight information, tools, and plans are communicated to the project team and the oversight committee to ensure a clear understanding of the role that oversight will play during the project. The Oversight Planning Process is supported by a number of sub processes and templates.  The sub processes and templates that support the Oversight Planning Process are as follows:

Sub Processes

Develop Oversight Plan

Complete Oversight Strategy Template

Complete Project Oversight Plan Document

Build Oversight Project Model

Communicate Project Oversight

Templates

Oversight Strategy Template

#### Oversight Implementation Process

The Oversight Implementation Process is the central process to the entire methodology. The implementation activities include the continuous monitoring of project performance, quality, and issues using the OPM. It also involves the reporting functions needed for communications of project health throughout the project lifecycle. The Oversight Implementation Process is supported by a number of sub processes and templates.  The sub processes and templates that support the Oversight Implementation Process are as follows:

Sub Processes

- Monitor Deliverable Dependencies

- Evaluate Deliverable Quality

- Report Oversight Status

- Complete Oversight Summary Report

- Complete Project Improvement Plan Template

- Complete Oversight Issues Report

- Complete Oversight Projects Rollup Report

- Monitor Issues/Actions

Templates

- Project Improvement Plan Template

#### Oversight Closeout Process

The Oversight Closeout Process is the final process is performed after final system implementation and completion of the project. It is designed to promote constant process improvement for the oversight methodology, the agency IT organization, and other affected Missouri IT program processes. It helps to ensure that Missouri will continuously improve its IT programs, which in turn improves the quality of Missouri’s IT systems. The Oversight Closeout Process is supported by a number of sub processes and templates.  The sub processes and templates that support the Oversight Closeout Process are as follows:

Sub Processes

- Perform Project Closeout

- Complete Process Improvement Template

Templates

- Process Improvement Template

#### Oversight Vitality Process

The Oversight Vitality Process is required to maintain the vitality of the Missouri Project Oversight Program.  The Project Oversight Manager generates process improvement reports that need to be addressed by the program.  Additionally, programmed and external trigger events to the vitality process need to be accommodated to ensure the continued viability of the program. At this time, the Project Oversight Program Vitality Process has been recognized but not defined.  Completion and incorporation into the Project Oversight Program is targeted for future addition to the program.

# Text boxes

Missouri Project Oversight Program

Risk Assessment

Performance Metrics

TCO/ROI

Project Oversight

Project Management Standing Committee (PMSC)

Architecture Review Committee (ARC)

Missouri

Information Technology Advisory Board (ITAB)

Project Oversight Manager

Prepared by

State of Missouri

Office of information Technology (OIT)

Complete Oversight Projects Rollup Report

Complete Oversight Issues Report

Oversight Controller

July 2002

Version: Initial Draft

Office of Information Technology

Part I

Project Oversight Administration

Chief Information Officer (CIO)

Complete Project Improvement Plan Template

Complete Oversight Summary Report

Report Oversight Status

Daily Project Environment

Project Team

Contractor Project Manager  (Optional)

Agency Project Manager

Project Oversight Committee / Oversight Reviewer

Oversight Summary Report Example

Oversight Issues Report Example

Project Improvement Plan Template

Ongoing Monitoring

Monthly Oversight Review

Oversight Projects Rollup Report Example

Office of Information Technology (OIT)

Monitor Deliverable Dependencies

Evaluate Deliverable Quality

Monitor Issues/ Actions

Implementation Process

Closeout Process

Project Completion

Process Improvement Report Template

Complete Process Improvement Report Template

Perform Project Closeout

Initiation Process

Planning Process

Vitality Process

Project Initiation

Project Information Template

Oversight Plan Document Example

Complete Project Information Template

Project Information Analysis

Initial Oversight Level Qualification

Project Oversight Model (OPM) Example

Oversight Strategy Template

Communicate Project Oversight

Build Oversight Project Model

Complete Project Oversight Plan Document

Complete Oversight Strategy Template

Develop Oversight Plan

| EXTERNAL RISK | High | 2 | 3 | 3 |
| --- | --- | --- | --- | --- |
|  | Med | 1 | 2 | 3 |
|  | Low | 0 | 1 | 2 |
|  | Low | Med | High |
|  | INTERNAL RISK |